## Raw_Metrics
Raw metrics | [34 empty] | Raw metrics resolved issues only | [8 empty] | Cycle time distribution
Issue key | Issue Type | Issue Summary | Creation Date | Resolution Date | In New Date | In Candidate Date | In Accepted Date | In in progress Date | In Code review Date | In Validation Date | In Merge Date | In Final check Date | In Done Date | In Closed Date | In On hold Date | In To Do Date | In Blocked Date | In Rejected Date | In New Time | In Candidate Time | In Accepted Time | In in progress Time | In Code review Time | In Validation Time | In Merge Time | In Final check Time | In Done Time | In Closed Time | In Blocked Time | In Rejected Time | In On hold Time | In To Do Time | Lead time | Cycle time | Issue key resolved | Resolution date for resolved | Cycle time resolved | Centile 20th | Centile 50th | Centile 80th | Lead time resolved | Centile 50th Lead Time | Centile 80th Lead Time | Cycle time Range | Cycle time Distribution
TDC-4662 | Work Item | [QA][SRE] AKS VMSS migration / DNS Switch to TPSVC services on K8s | 2020-9-1 | 2020-9-3 | 2020-9-1 17:35:59 |  | 2020-9-1 17:36:04 | 2020-9-1 17:36:09 |  | 2020-9-3 15:51:56 | [8 empty] | 0.20647 |  | 5.787e-05 | 5.787e-05 |  | 1.9276 | [8 empty] | 2.1342 | 1.9277 | TDC-4494 | 2020-7-15 | 0.2 | 1.8982 | 6.7447 | 13.1933 | 4.79 | 15.1708 | 46.3908 | 0 | 23
TDC-4121 | Work Item | [QA][API] Validate auth0 deployment in AZ Prods stacks | 2020-5-15 | 2020-8-12 | 2020-8-5 09:03:45 |  | 2020-8-5 09:03:51 | 2020-8-12 08:49:33 |  | 2020-8-12 17:33:02 |  |  |  |  | 2020-8-11 17:01:59 |  |  |  | 81.8305 |  | 6.9444e-05 | 6.7144 |  | 0.36353 | [6 empty] | 0.27567 |  | 89.1842 | 7.0779 | TDC-4418 | 2020-7-17 | 1.99 | 1.8982 | 6.7447 | 13.1933 | 8.04 | 15.1708 | 46.3908 | 3 | 12
TDC-4479 | Work Item | [QA][API] GLOBAL QUALITY INFO OF CURRENT SAMPLE | 2020-7-10 | 2020-8-12 | 2020-7-30 16:51:55 |  | 2020-8-10 13:35:06 | 2020-8-10 16:27:57 |  | 2020-8-12 13:03:49 | 2020-8-12 13:04:00 | [7 empty] | 20.0489 |  | 10.8633 | 0.12003 |  | 1.8582 | 0.00012731 | [7 empty] | 32.8906 | 1.9784 | TDC-4501 | 2020-7-17 | 0.38 | 1.8982 | 6.7447 | 13.1933 | 1.38 | 15.1708 | 46.3908 | 6 | 11
TDC-4552 | Bug | API automated tests are broken on Pagination feature when using stack with broken entities references | 2020-7-27 |  | 2020-7-28 20:27:08 |  | 2020-7-28 23:03:04 | [11 empty] | 1.2836 |  | 0.10829 | [12 empty] | 0 | TDC-4350 | 2020-7-20 | 12.05 | 1.8982 | 6.7447 | 13.1933 | 19.07 | 15.1708 | 46.3908 | 9 | 10
TDC-4481 | Work Item | [QA][UI] GLOBAL QUALITY INFO OF CURRENT SAMPLE | 2020-7-10 | 2020-8-18 | 2020-7-30 16:51:43 |  | 2020-8-13 09:29:14 | 2020-8-18 17:39:59 |  | 2020-8-18 17:40:06 | 2020-8-18 17:42:35 | [7 empty] | 20.0463 |  | 13.6927 | 5.3408 |  | 8.1019e-05 | 0.0017245 | [7 empty] | 39.0816 | 5.3426 | TDC-4226 | 2020-7-20 | 23.74 | 1.8982 | 6.7447 | 13.1933 | 33.72 | 15.1708 | 46.3908 | 12 | 9
TDC-4081 | Bug | [Front] The raw sample view is not fed with the right data | 2020-5-6 | 2020-9-2 | 2020-7-24 16:00:09 | 2020-8-7 11:57:36 | 2020-8-25 11:57:32 | 2020-8-26 11:42:26 | 2020-8-26 14:29:37 | 2020-9-1 16:00:20 | 2020-9-2 15:12:22 | 2020-9-2 15:12:31 | [6 empty] | 79.1897 | 13.8316 | 18 | 0.98951 | 0.1161 | 6.063 | 0.96669 | 0.00010417 | [6 empty] | 119.1566 | 8.1354 | TDC-4344 | 2020-7-21 | 9.92 | 1.8982 | 6.7447 | 13.1933 | 20.67 | 15.1708 | 46.3908 | 15 | 6
TDC-4551 | Bug | Can't authenticate anymore to Azure Sandbox TDC | 2020-7-27 | 2020-7-28 | 2020-7-28 11:02:31 | [13 empty] | 0.89922 | [13 empty] | 0.89922 | 0 | TDC-4351 | 2020-7-24 | 17.28 | 1.8982 | 6.7447 | 13.1933 | 23.01 | 15.1708 | 46.3908 | 18 | 0
TDC-4642 | Work Item | [Back] Add schema to dataset-samples response | 2020-8-20 |  | 2020-8-20 16:18:14 |  | 2020-9-1 11:59:36 | 2020-9-2 18:10:29 | 2020-9-3 11:37:32 | 2020-9-7 17:57:31 | [8 empty] | 0.17323 |  | 11.8204 | 1.2576 | 0.72712 | 4.2639 | [9 empty] | 6.2486 | TDC-4535 | 2020-7-24 | 1.21 | 1.8982 | 6.7447 | 13.1933 | 1.25 | 15.1708 | 46.3908 | 21 | 1
TDC-3796 | New Feature | [Front] Improve Pendo Analytics | 2020-3-17 | 2020-9-2 | 2020-7-28 11:54:53 | 2020-8-7 10:58:04 | 2020-8-26 09:42:06 | 2020-8-26 09:42:18 | 2020-8-28 10:10:39 | 2020-9-2 09:32:07 | 2020-9-2 15:13:10 | 2020-9-2 19:25:27 |  |  | 2020-7-28 11:45:36 |  |  |  | 13.5574 | 9.9605 | 18.9472 | 0.00013889 | 2.0197 | 4.9732 | 0.23684 | 0.1752 |  |  |  |  | 119.104 |  | 168.9743 | 7.4051 | TDC-4342 | 2020-7-24 | 3.15 | 1.8982 | 6.7447 | 13.1933 | 24.12 | 15.1708 | 46.3908 | 24 | 1
TDC-3951 | New Feature | [Back] Migrate to DQ architecture v2 - semantic dictionary | 2020-4-16 | 2020-7-28 | 2020-6-22 08:32:12 |  | 2020-6-30 10:49:46 | 2020-7-9 10:30:30 | 2020-7-16 17:08:58 | 2020-7-21 16:32:47 | 2020-7-22 14:43:49 | 2020-7-28 09:46:31 | [6 empty] | 66.7039 |  | 8.0955 | 8.9866 | 7.2767 | 4.9749 | 0.92433 | 5.7935 | [6 empty] | 102.7555 | 27.9561 | TDC-4519 | 2020-7-24 | 3.28 | 1.8982 | 6.7447 | 13.1933 | 4 | 15.1708 | 46.3908 | 27 | 2
TDC-4523 | Bug | WS does not display freshly created datasets from demo content | 2020-7-21 | 2020-7-21 | 2020-7-21 10:24:46 | [13 empty] | 0.054572 | [13 empty] | 0.054572 | 0 | TDC-4498 | 2020-7-24 | 3.23 | 1.8982 | 6.7447 | 13.1933 | 8.8 | 15.1708 | 46.3908 | 30 | 0
TDC-3834 | Work Item | [SRE] Implement HorizontalPodAutoscaler for Helm charts | 2020-3-26 | 2020-7-30 | 2020-4-14 14:18:47 |  | 2020-4-14 14:18:52 | 2020-7-16 10:36:32 |  | 2020-7-21 15:30:50 | 2020-7-21 15:31:00 | 2020-7-30 16:43:49 | [6 empty] | 18.8138 |  | 5.787e-05 | 92.8456 |  | 5.2044 | 0.00011574 | 9.0506 | [6 empty] | 125.9145 | 107.1007 | TDC-4538 | 2020-7-24 | 1.01 | 1.8982 | 6.7447 | 13.1933 | 1.02 | 15.1708 | 46.3908
TDC-4366 | Bug | [Front] Websocket does not display directly the Demo Content's created datasets | 2020-7-2 | 2020-7-28 | 2020-7-15 10:10:00 |  | 2020-7-15 10:10:05 | 2020-7-16 11:50:26 | 2020-7-16 14:07:59 | 2020-7-24 17:21:21 | 2020-7-27 17:18:08 | 2020-7-28 11:50:35 | [6 empty] | 12.7869 |  | 5.787e-05 | 1.0697 | 0.095521 | 8.1343 | 2.9978 | 0.77253 | [6 empty] | 25.8567 | 13.0698 | TDC-4331 | 2020-7-27 | 9.84 | 1.8982 | 6.7447 | 13.1933 | 27.99 | 15.1708 | 46.3908
TDC-4494 | Bug | [Backend] Can't access to app-switcher (INT / Az Sandbox) | 2020-7-10 | 2020-7-15 | 2020-7-15 10:08:40 |  | 2020-7-15 10:08:44 | 2020-7-15 11:02:26 |  | 2020-7-15 14:55:40 | [8 empty] | 4.5942 |  | 4.6296e-05 | 0.037292 |  | 0.16197 | [8 empty] | 4.7935 | 0.19926 | TDC-4252 | 2020-7-27 | 28.05 | 1.8982 | 6.7447 | 13.1933 | 39.12 | 15.1708 | 46.3908
TDC-4143 | Bug | [Front] Form freezes when editing a shared dataset as READER using Local Connection | 2020-5-20 | 2020-8-26 | 2020-7-24 16:44:36 | 2020-8-7 15:49:50 | 2020-8-20 16:07:04 | 2020-8-26 14:40:01 |  | 2020-8-26 14:40:37 | [8 empty] | 64.7424 | 13.962 | 13.012 | 0.0059838 |  | 5.934 | [8 empty] | 97.6563 | 5.94 | TDC-3951 | 2020-7-28 | 27.96 | 1.8982 | 6.7447 | 13.1933 | 102.76 | 15.1708 | 46.3908
TDC-4504 | Work Item | [Back] [Engineering] Trust score V2 : enrichment with new metrics | 2020-7-16 | 2020-8-19 | 2020-7-16 12:55:44 | 2020-7-23 14:39:31 | 2020-8-4 14:37:43 | 2020-8-5 18:17:12 | 2020-8-19 10:02:43 | 2020-8-19 10:02:55 |  |  |  |  | 2020-7-21 15:46:14 |  |  |  | 0.012407 | 2.0681 | 17.0027 | 1.1524 | 13.6566 | 0.00013889 | [6 empty] | 8.1019e-05 |  | 33.8924 | 14.8092 | TDC-4366 | 2020-7-28 | 13.07 | 1.8982 | 6.7447 | 13.1933 | 25.86 | 15.1708 | 46.3908
TDC-4505 | Work Item | [Front & Back] [Engineering] Trust score : data visualization | 2020-7-16 | 2020-8-20 | 2020-7-16 12:55:52 | 2020-7-23 14:46:41 | 2020-8-4 11:38:14 | 2020-8-18 11:27:39 |  | 2020-8-20 10:20:41 |  |  |  |  | 2020-7-21 15:47:19 |  |  |  | 0.0022338 | 2.1211 | 16.825 | 13.9927 |  | 1.9535 | [6 empty] | 4.6296e-05 |  | 34.8945 | 15.9461 | TDC-3006 | 2020-7-28 | 26.02 | 1.8982 | 6.7447 | 13.1933 | 307.03 | 15.1708 | 46.3908
TDC-4329 | Work Item | [Back] Trust score - Automate unit tests | 2020-6-29 | 2020-8-6 | 2020-7-15 09:13:40 |  | 2020-8-4 14:24:07 | 2020-8-6 10:30:14 | 2020-8-6 12:11:08 | 2020-8-6 12:12:05 | [8 empty] | 15.7806 |  | 20.2156 | 1.8376 | 0.070069 | 0.00065972 | [8 empty] | 37.9045 | 1.9083 | TDC-4509 | 2020-7-28 | 11.06 | 1.8982 | 6.7447 | 13.1933 | 11.71 | 15.1708 | 46.3908
TDC-4330 | New Feature | [Back] Trust score - Implementing the formula V1 | 2020-6-29 | 2020-8-18 | 2020-7-15 09:13:59 |  | 2020-8-5 10:02:39 | 2020-8-7 17:05:13 | 2020-8-12 13:54:35 | 2020-8-17 16:15:49 | 2020-8-18 17:36:03 | 2020-8-18 17:38:57 | [6 empty] | 15.7776 |  | 21.0338 | 2.2934 | 4.8676 | 5.0981 | 1.0557 | 0.0020139 | [6 empty] | 50.1283 | 13.3169 | TDC-4556 | 2020-7-28 | 0.73 | 1.8982 | 6.7447 | 13.1933 | 0.74 | 15.1708 | 46.3908
TDC-4333 | Work Item | [Back] Trust score - Compute trust score using column type based quality score | 2020-6-29 | 2020-8-3 | 2020-7-29 14:11:00 | 2020-7-30 15:21:20 | 2020-8-3 17:23:35 | [11 empty] | 29.9763 | 1.0488 | 4.0849 | [11 empty] | 35.11 | 0 | TDC-4544 | 2020-7-28 | 3.97 | 1.8982 | 6.7447 | 13.1933 | 4.01 | 15.1708 | 46.3908
TDC-4231 | New Feature | [Front] Get all datasets with the new datasets api | 2020-6-17 | 2020-8-19 | 2020-7-23 14:16:43 | 2020-7-23 14:21:30 | 2020-8-4 11:22:17 | 2020-8-6 15:10:23 | 2020-8-6 16:46:48 | 2020-8-13 23:38:28 | 2020-8-19 09:59:34 | 2020-8-19 15:32:55 | [6 empty] | 36.1615 | 0.0033218 | 11.8755 | 2.1584 | 0.066956 | 7.2859 | 5.4313 | 0.23149 | [6 empty] | 63.2144 | 15.1741 | TDC-4520 | 2020-7-28 | 7.67 | 1.8982 | 6.7447 | 13.1933 | 7.69 | 15.1708 | 46.3908
TDC-4334 | Work Item | [Front] Trust score - Do not apply transformation from 100based to 5based trustscore with new client | 2020-6-29 | 2020-8-19 | 2020-7-21 15:32:18 | 2020-7-23 14:21:47 | 2020-8-5 10:09:15 | 2020-8-6 16:34:11 | 2020-8-6 16:46:50 | 2020-8-13 09:25:30 | 2020-8-19 09:59:42 | 2020-8-19 14:03:50 | [6 empty] | 22.0274 | 1.951 | 12.8246 | 1.2673 | 0.0087847 | 6.6935 | 6.0237 | 0.16954 | [6 empty] | 50.9659 | 14.1629 | TDC-4559 | 2020-7-28 | 0.1 | 1.8982 | 6.7447 | 13.1933 | 0.69 | 15.1708 | 46.3908
TDC-4331 | Work Item | [Back] Trust score - Change API for new clients to return trust score between 0 & 5 | 2020-6-29 | 2020-7-27 | 2020-7-17 14:22:01 |  | 2020-7-17 18:18:44 | 2020-7-17 18:18:49 | 2020-7-21 09:05:09 | 2020-7-21 10:55:56 | 2020-7-23 08:40:35 | 2020-7-27 14:26:37 | [6 empty] | 17.9898 |  | 0.16439 | 5.787e-05 | 3.6155 | 0.076933 | 1.906 | 4.2403 | [6 empty] | 27.993 | 9.8388 | TDC-4516 | 2020-7-29 | 2.01 | 1.8982 | 6.7447 | 13.1933 | 8.99 | 15.1708 | 46.3908
TDC-4350 | Work Item | [Engineering] [QA] Map QA JIRAs with P1/P2 list then sort them in QA backlog | 2020-7-1 | 2020-7-20 | 2020-7-8 14:46:22 |  | 2020-7-8 14:46:30 | 2020-7-9 17:55:47 | 2020-7-10 18:09:43 | 2020-7-10 18:09:52 | 2020-7-10 18:09:57 | 2020-7-20 15:56:06 | 2020-7-20 15:57:21 | [5 empty] | 7.0167 |  | 9.2593e-05 | 1.1314 | 1.0097 | 0.00010417 | 5.787e-05 | 9.907 | 0.00086806 | [5 empty] | 19.0651 | 12.0483 | TDC-4571 | 2020-7-30 | 1.3 | 1.8982 | 6.7447 | 13.1933 | 2.01 | 15.1708 | 46.3908
TDC-4615 | Work Item | [Improvement][QA][UI] Cleaning existing entities before launching ui tests | 2020-8-6 | 2020-8-6 | 2020-8-6 09:54:01 |  | 2020-8-6 09:54:06 | 2020-8-6 09:54:11 |  | 2020-8-6 12:30:59 | 2020-8-6 12:31:03 | 2020-8-6 12:31:12 | [6 empty] | 0.00013889 |  | 5.787e-05 | 5.787e-05 |  | 0.10889 | 4.6296e-05 | 0.00010417 | [6 empty] | 0.10929 | 0.1091 | TDC-3967 | 2020-7-30 | 13.93 | 1.8982 | 6.7447 | 13.1933 | 100.72 | 15.1708 | 46.3908
TDC-4344 | Bug | [Sharing] Unable to re-init an entity after delete | 2020-6-30 | 2020-7-21 | 2020-7-1 15:57:24 | 2020-7-7 08:24:30 | 2020-7-7 08:24:34 | 2020-7-20 14:39:55 | 2020-7-21 09:24:10 | 2020-7-21 09:24:20 | 2020-7-16 10:08:47 | 2020-7-16 11:29:49 | 2020-7-20 14:27:32 | [5 empty] | 0.94001 | 5.6855 | 4.6296e-05 | 1.4124 | 0.78073 | 6.9099 | 0.75874 | 0.056273 | 4.1234 | [5 empty] | 20.667 | 9.9181 | TDC-4497 | 2020-7-30 | 6.05 | 1.8982 | 6.7447 | 13.1933 | 15.17 | 15.1708 | 46.3908
TDC-4351 | Bug | [Dataset] Unable to recreate a connection or a dataset with the same id after delete | 2020-7-1 | 2020-7-24 | 2020-7-1 15:57:31 | 2020-7-7 08:29:43 | 2020-7-7 08:29:53 | 2020-7-21 14:21:18 |  | 2020-7-21 14:21:23 | 2020-7-22 14:43:37 | 2020-7-24 15:12:08 | [6 empty] | 0.04463 | 5.689 | 0.00011574 | 14.0954 |  | 0.14867 | 1.0154 | 2.0198 | [6 empty] | 23.0131 | 17.2793 | TDC-4499 | 2020-7-30 | 5.89 | 1.8982 | 6.7447 | 13.1933 | 14.01 | 15.1708 | 46.3908
TDC-4521 | Bug | [Front][Dataset] Improve quality tile for API created datasets | 2020-7-20 | 2020-8-3 | 2020-7-23 17:28:49 |  | 2020-7-23 17:28:57 | 2020-7-23 17:29:25 | 2020-7-27 15:44:11 | 2020-8-3 14:16:30 | [8 empty] | 2.9691 |  | 9.2593e-05 | 0.00032407 | 3.9269 | 6.9391 | [8 empty] | 13.8355 | 10.8664 | TDC-4542 | 2020-7-30 | 1.31 | 1.8982 | 6.7447 | 13.1933 | 6.29 | 15.1708 | 46.3908
TDC-4634 | Bug | SSRF on Data Inventory leaking AWS metadata | 2020-7-2 | 2020-8-17 | 2020-8-14 18:16:36 | 2020-8-17 07:51:15 | 2020-8-17 11:24:48 | 2020-8-17 11:24:54 |  | 2020-8-17 11:25:23 |  |  | 2020-8-28 15:26:02 |  |  | 2020-8-14 17:53:10 |  |  | 0.016273 | 2.5657 | 0.1483 | 6.9444e-05 |  | 0.00033565 |  |  | 11.1671 |  |  |  |  | 43.6054 | 46.3361 | 0.00040509 | TDC-4332 | 2020-7-31 | 11.34 | 1.8982 | 6.7447 | 13.1933 | 31.75 | 15.1708 | 46.3908
TDC-4535 | Work Item | [Release] Sharing 1.22.1 | 2020-7-23 | 2020-7-24 | 2020-7-23 11:09:01 |  | 2020-7-23 12:00:13 | 2020-7-23 12:00:19 |  | 2020-7-24 11:06:21 | 2020-7-24 14:54:47 | 2020-7-24 17:03:03 | [6 empty] | 0.0077315 |  | 0.035556 | 6.9444e-05 |  | 0.96252 | 0.15863 | 0.089074 | [6 empty] | 1.2536 | 1.2103 | TDC-4543 | 2020-7-31 | 1.89 | 1.8982 | 6.7447 | 13.1933 | 6.87 | 15.1708 | 46.3908
TDC-4418 | Work Item | [Release] Sharing 1.22.0 | 2020-7-9 | 2020-7-17 | 2020-7-10 17:37:47 |  | 2020-7-15 09:56:14 | 2020-7-15 09:56:21 |  | 2020-7-15 16:53:32 | 2020-7-16 10:08:32 | 2020-7-17 09:38:30 | [6 empty] | 1.3684 |  | 4.6795 | 8.1019e-05 |  | 0.28971 | 0.71875 | 0.97914 | [6 empty] | 8.0356 | 1.9877 | TDC-4577 | 2020-7-31 | 2.08 | 1.8982 | 6.7447 | 13.1933 | 2.19 | 15.1708 | 46.3908
TDC-4501 | Work Item | [Release] Rating 1.15.0 | 2020-7-16 | 2020-7-17 | 2020-7-17 09:44:32 |  | 2020-7-17 09:44:36 | 2020-7-17 09:44:41 |  | 2020-7-17 15:48:09 | 2020-7-17 18:43:03 | 2020-7-17 18:51:11 | [6 empty] | 0.99948 |  | 4.6296e-05 | 5.787e-05 |  | 0.25241 | 0.12146 | 0.0056481 | [6 empty] | 1.3791 | 0.37957 | TDC-4521 | 2020-8-3 | 10.87 | 1.8982 | 6.7447 | 13.1933 | 13.84 | 15.1708 | 46.3908
TDC-4226 | Work Item | [Engineering][QA] Handle tacokit migration task for connector | 2020-6-16 | 2020-7-20 | 2020-6-26 16:23:21 |  | 2020-6-26 16:23:34 | 2020-7-20 10:05:26 |  | 2020-7-20 10:05:36 | [8 empty] | 9.9812 |  | 0.00015046 | 23.7374 |  | 0.00011574 | [8 empty] | 33.7189 | 23.7375 | TDC-4595 | 2020-8-3 | 4.15 | 1.8982 | 6.7447 | 13.1933 | 4.3 | 15.1708 | 46.3908
TDC-4252 | Work Item | [Back] Add pagination to dataset list & dataset-search | 2020-6-18 | 2020-7-27 | 2020-6-22 08:32:28 |  | 2020-6-29 12:22:39 | 2020-7-3 10:03:21 | 2020-7-20 14:40:13 | 2020-7-21 21:17:51 | 2020-7-23 08:40:22 | 2020-7-27 13:40:43 | [6 empty] | 3.9034 |  | 7.1598 | 3.9033 | 17.1923 | 1.2761 | 1.474 | 4.2086 | [6 empty] | 39.1174 | 28.0542 | TDC-4291 | 2020-8-4 | 0.15 | 1.8982 | 6.7447 | 13.1933 | 46.98 | 15.1708 | 46.3908
TDC-3991 | Bug | [Back] Element in a list starting with $ raise a cast exception | 2020-4-24 | 2020-8-25 | 2020-7-24 16:12:48 | 2020-8-5 16:35:10 | 2020-8-20 15:51:34 | 2020-8-20 15:51:39 |  | 2020-8-25 17:31:08 | [8 empty] | 91.2683 | 12.0155 | 14.9697 | 5.787e-05 |  | 5.0691 | [8 empty] | 123.3227 | 5.0691 | TDC-4597 | 2020-8-4 | 4.04 | 1.8982 | 6.7447 | 13.1933 | 4.33 | 15.1708 | 46.3908
TDC-4251 | New Feature | [Front] [Security] Automate SCA & SAST scans. | 2020-6-18 | 2020-8-27 | 2020-7-30 15:49:46 | 2020-7-30 15:49:56 | 2020-8-10 15:38:55 | 2020-8-20 10:00:07 | 2020-8-27 10:16:23 | 2020-8-27 10:16:38 | [8 empty] | 42.212 | 0.00011574 | 10.9923 | 9.7647 | 7.0113 | 0.00017361 | [8 empty] | 69.9806 | 16.7762 | TDC-4329 | 2020-8-6 | 1.91 | 1.8982 | 6.7447 | 13.1933 | 37.9 | 15.1708 | 46.3908
TDC-4407 | Work Item | [Provisioning Sprint 48] Manage unexpected / unplanned subjects | 2020-7-7 | 2020-7-30 | 2020-7-15 09:15:45 |  | 2020-7-30 16:43:39 | [11 empty] | 7.7007 |  | 15.311 | [11 empty] | 23.0117 | 0 | TDC-4615 | 2020-8-6 | 0.11 | 1.8982 | 6.7447 | 13.1933 | 0.11 | 15.1708 | 46.3908
TDC-4416 | Work Item | [Provisioning Sprint 49] Manage unexpected / unplanned subjects | 2020-7-8 | 2020-8-20 | 2020-8-20 10:49:03 | [13 empty] | 42.8391 | [13 empty] | 42.8391 | 0 | TDC-4405 | 2020-8-6 | 6.74 | 1.8982 | 6.7447 | 13.1933 | 29.73 | 15.1708 | 46.3908
TDC-4571 | Work Item | [Release] Data Inventory 1.27.0 | 2020-7-28 | 2020-7-30 | 2020-7-28 17:43:52 |  | 2020-7-29 10:02:56 | 2020-7-29 10:03:03 |  | 2020-7-29 13:23:37 | 2020-7-30 09:45:18 | 2020-7-30 17:07:48 | [6 empty] | 0.039039 |  | 0.67991 | 8.1019e-05 |  | 0.13928 | 0.84839 | 0.30729 | [6 empty] | 2.014 | 1.295 | TDC-4607 | 2020-8-7 | 2.96 | 1.8982 | 6.7447 | 13.1933 | 2.97 | 15.1708 | 46.3908
TDC-4332 | Work Item | [Back] Trust score - Compute global quality on columns based on types | 2020-6-29 | 2020-7-31 | 2020-7-20 16:46:24 |  | 2020-7-20 16:46:29 | 2020-7-30 13:58:27 | 2020-7-29 10:00:53 | 2020-7-30 16:07:41 | 2020-7-30 16:46:04 | 2020-7-31 08:46:54 | 2020-7-30 13:58:21 |  | 2020-7-17 10:20:39 |  |  |  | 19.0402 |  | 1.3698 | 7.6872 | 1.708 | 1.2538 | 0.026655 | 0.66725 | 0.00083333 |  |  |  | 0.00012731 |  | 31.7539 | 11.343 | TDC-4121 | 2020-8-12 | 7.08 | 1.8982 | 6.7447 | 13.1933 | 89.18 | 15.1708 | 46.3908
TDC-4603 | Work Item | [Provisioning Sprint 50] Manage unexpected / unplanned subjects | 2020-8-3 |  | 2020-8-21 07:53:49 | [13 empty] | 17.6882 | [14 empty] | 0 | TDC-4479 | 2020-8-12 | 1.98 | 1.8982 | 6.7447 | 13.1933 | 32.89 | 15.1708 | 46.3908
TDC-4680 | Work Item | [Release] Sharing 1.23.0 | 2020-9-7 |  | 2020-9-7 11:47:38 |  | 2020-9-7 11:47:42 | 2020-9-7 11:47:52 |  | 2020-9-8 09:56:47 | 2020-9-9 10:56:56 | [7 empty] | 0.0010764 |  | 4.6296e-05 | 0.00011574 |  | 0.92286 | 1.0418 | [8 empty] | 1.9647 | TDC-4563 | 2020-8-13 | 8.91 | 1.8982 | 6.7447 | 13.1933 | 16.08 | 15.1708 | 46.3908
TDC-4194 | New Feature | [Back][Attributes] Create/Update CAV automatically when CAD default value is settled/updated | 2020-6-8 |  | 2020-6-30 16:45:57 | 2020-8-5 15:43:24 | 2020-8-25 11:51:26 | 2020-8-28 17:36:25 | 2020-9-4 11:21:14 | 2020-9-8 14:58:11 | [8 empty] | 22.0668 | 35.9566 | 19.8389 | 3.2396 | 6.7395 | 4.1507 | [9 empty] | 14.1297 | TDC-4621 | 2020-8-13 | 2.86 | 1.8982 | 6.7447 | 13.1933 | 3.04 | 15.1708 | 46.3908
TDC-3006 | Bug | [Front] _name for widget: datalist are not sent to backend in creation and edition form | 2019-9-25 | 2020-7-28 | 2020-6-26 14:33:11 |  | 2020-7-2 11:34:19 | 2020-7-10 17:04:46 | 2020-7-16 10:21:52 | 2020-7-27 11:21:24 | 2020-7-27 17:18:03 | 2020-7-28 11:57:50 | [6 empty] | 275.1332 |  | 5.8758 | 8.2295 | 5.7202 | 11.0413 | 0.24767 | 0.77763 | [6 empty] | 307.0253 | 26.0163 | TDC-4481 | 2020-8-18 | 5.34 | 1.8982 | 6.7447 | 13.1933 | 39.08 | 15.1708 | 46.3908
TDC-3967 | New Feature | [Front] Search by global quality from sample facet | 2020-4-20 | 2020-7-30 | 2020-6-23 16:58:08 | 2020-6-30 11:44:15 | 2020-7-16 11:51:12 | 2020-7-24 12:19:27 | 2020-7-28 16:47:48 | 2020-7-29 12:58:21 | 2020-7-30 09:46:51 | 2020-7-30 10:10:46 |  |  | 2020-7-17 10:51:34 |  |  |  | 64.0065 | 6.782 | 16.0048 | 8.0184 | 4.1864 | 0.84066 | 0.86701 | 0.016609 |  |  |  |  | 0.0012153 |  | 100.7236 | 13.929 | TDC-4330 | 2020-8-18 | 13.32 | 1.8982 | 6.7447 | 13.1933 | 50.13 | 15.1708 | 46.3908
TDC-4219 | New Feature | [SRE] Update infrastructure ( Flux/Helm Chart ) to remove the rating-provisioner and use the rating as the rating-provisioner | 2020-6-16 | 2020-8-4 | 2020-7-29 14:09:20 | 2020-8-3 10:37:29 | 2020-8-4 17:25:58 | 2020-8-4 17:26:10 |  | 2020-8-4 17:26:23 | [8 empty] | 43.1973 | 4.8529 | 1.2837 | 0.00013889 |  | 0.00015046 | [8 empty] | 49.3342 | 0.00028935 | TDC-4545 | 2020-8-18 | 12.03 | 1.8982 | 6.7447 | 13.1933 | 24.79 | 15.1708 | 46.3908
TDC-4291 | New Feature | [SRE] Update infrastructure ( Flux/Helm Chart ) to remove the dataset-provisioner and use the dataset as the dataset-provisioner | 2020-6-18 | 2020-8-4 | 2020-7-29 14:09:30 | 2020-8-3 10:39:35 | 2020-8-4 13:50:59 | 2020-8-4 17:26:33 |  | 2020-8-4 17:26:41 | [8 empty] | 40.8399 | 4.8542 | 1.1329 | 0.1497 |  | 9.2593e-05 | [8 empty] | 46.9769 | 0.14979 | TDC-4345 | 2020-8-18 | 15.49 | 1.8982 | 6.7447 | 13.1933 | 48.27 | 15.1708 | 46.3908
TDC-4509 | Bug | [Front] sharing status in dataset list is not updated when dataset is shared | 2020-7-16 | 2020-7-28 | 2020-7-17 10:23:19 |  | 2020-7-17 10:23:23 | 2020-7-17 10:32:59 | 2020-7-22 11:52:57 | 2020-7-27 10:05:09 | 2020-7-27 17:18:11 | 2020-7-28 11:53:36 | [6 empty] | 0.64775 |  | 4.6296e-05 | 0.0066667 | 5.0555 | 4.9251 | 0.30072 | 0.77459 | [6 empty] | 11.7105 | 11.0627 | TDC-4632 | 2020-8-18 | 1.29 | 1.8982 | 6.7447 | 13.1933 | 4.29 | 15.1708 | 46.3908
TDC-4545 | New Feature | [Back] Integrate TSD consumer 5.1.1 in dataset | 2020-7-24 | 2020-8-18 | 2020-7-24 17:22:15 | 2020-7-29 16:19:29 | 2020-8-6 11:02:50 | 2020-8-6 15:35:50 | 2020-8-10 15:26:35 | 2020-8-17 17:01:43 | 2020-8-18 11:43:31 | 2020-8-18 11:46:23 | [6 empty] | 0.026088 | 4.9564 | 7.7801 | 0.18958 | 3.9936 | 7.0661 | 0.77903 | 0.0019907 | [6 empty] | 24.7928 | 12.0302 | TDC-4504 | 2020-8-19 | 14.81 | 1.8982 | 6.7447 | 13.1933 | 33.89 | 15.1708 | 46.3908
TDC-4595 | Bug | [Dataset][Back] Date types are detected as "string" | 2020-7-30 | 2020-8-3 | 2020-7-30 18:23:35 |  | 2020-7-30 18:23:40 | 2020-7-31 09:38:22 |  | 2020-7-31 18:17:03 | 2020-8-3 17:48:24 | 2020-8-3 21:53:05 | [6 empty] | 0.15874 |  | 5.787e-05 | 0.63521 |  | 0.3602 | 2.9801 | 0.16992 | [6 empty] | 4.3042 | 4.1454 | TDC-4231 | 2020-8-19 | 15.17 | 1.8982 | 6.7447 | 13.1933 | 63.21 | 15.1708 | 46.3908
TDC-4355 | New Feature | [Front] Implement the lazyloading on the dataset view | 2020-7-1 | 2020-8-19 | 2020-7-16 13:29:32 | 2020-7-16 15:15:29 | 2020-8-6 21:13:40 | 2020-8-14 15:59:10 |  | 2020-8-18 18:09:02 | 2020-8-19 09:59:50 | 2020-8-19 15:31:45 | [6 empty] | 14.8369 | 0.073576 | 21.2487 | 7.7816 |  | 4.0902 | 0.66028 | 0.2305 | [6 empty] | 48.9218 | 12.7626 | TDC-4334 | 2020-8-19 | 14.16 | 1.8982 | 6.7447 | 13.1933 | 50.97 | 15.1708 | 46.3908
TDC-4546 | New Feature | [Back] Trust score Formula V2 : enrichment with description, tags and attributes | 2020-7-24 | 2020-9-7 | 2020-8-20 15:24:07 | 2020-8-20 15:25:30 | 2020-8-26 10:31:17 | 2020-8-31 09:42:52 | 2020-9-1 16:55:34 | 2020-9-4 09:27:45 | 2020-9-7 09:45:34 | 2020-9-7 09:48:06 | [6 empty] | 26.9343 | 0.00096065 | 5.7957 | 4.9664 | 1.3005 | 2.689 | 3.0124 | 0.0017593 | [6 empty] | 44.7009 | 11.97 | TDC-4355 | 2020-8-19 | 12.76 | 1.8982 | 6.7447 | 13.1933 | 48.92 | 15.1708 | 46.3908
TDC-4604 | Work Item | [QA] Trust score Formula V2: Automate Validation Tests | 2020-8-3 | 2020-9-7 | 2020-8-17 16:09:09 |  | 2020-8-27 10:03:43 | 2020-8-31 01:54:15 |  | 2020-9-4 09:34:37 | 2020-9-7 10:07:33 | [7 empty] | 14.0199 |  | 9.7462 | 3.6601 |  | 4.3197 | 3.0229 | [7 empty] | 34.7688 | 11.0027 | TDC-4609 | 2020-8-19 | 14.04 | 1.8982 | 6.7447 | 13.1933 | 14.27 | 15.1708 | 46.3908
TDC-4605 | New Feature | [Front] Trust score data visualization : creating the dedicated talend UI component | 2020-8-3 |  | 2020-8-26 09:08:44 |  | 2020-8-31 10:08:43 | 2020-9-4 16:59:41 | [10 empty] | 22.7144 |  | 5.0417 | 4.2854 | [11 empty] | 4.2854 | TDC-4623 | 2020-8-19 | 9.02 | 1.8982 | 6.7447 | 13.1933 | 9.04 | 15.1708 | 46.3908
TDC-4536 | New Feature | [Back] Trust score api payload with axes. | 2020-7-23 | 2020-9-7 | 2020-8-20 15:38:06 |  | 2020-8-26 10:21:09 | 2020-8-27 10:18:01 | 2020-8-31 17:00:46 | 2020-9-4 11:51:14 | 2020-9-7 09:52:34 | 2020-9-7 09:54:18 | [6 empty] | 28.0436 |  | 5.7799 | 0.99782 | 4.2797 | 3.785 | 2.9176 | 0.0012037 | [6 empty] | 45.8048 | 11.9814 | TDC-4624 | 2020-8-19 | 8.83 | 1.8982 | 6.7447 | 13.1933 | 8.84 | 15.1708 | 46.3908
TDC-4572 | Work Item | [Back] [Engineering] Trust score V3 : enrichment with new metrics | 2020-7-28 |  | 2020-8-4 17:52:45 |  | 2020-9-2 09:36:47 | 2020-9-3 15:59:04 | 2020-9-9 10:06:54 | [9 empty] | 6.9743 |  | 28.6556 | 1.2655 | 5.7554 | [10 empty] | 7.0209 | TDC-4625 | 2020-8-19 | 8.83 | 1.8982 | 6.7447 | 13.1933 | 8.84 | 15.1708 | 46.3908
TDC-4497 | New Feature | [Back] Search by trustscore from sample facet, modify the step | 2020-7-15 | 2020-7-30 | 2020-7-24 12:04:00 | 2020-7-24 12:04:42 | 2020-7-24 16:43:53 | 2020-7-24 17:05:46 | 2020-7-24 17:28:48 | 2020-7-29 15:59:31 | 2020-7-30 16:45:36 | 2020-7-30 17:57:10 | [6 empty] | 8.9255 | 0.00048611 | 0.19388 | 0.015197 | 0.015995 | 4.938 | 1.032 | 0.049699 | [6 empty] | 15.1708 | 6.0509 | TDC-4505 | 2020-8-20 | 15.95 | 1.8982 | 6.7447 | 13.1933 | 34.89 | 15.1708 | 46.3908
TDC-4499 | New Feature | [Front] Search by trustscore from sample facet | 2020-7-16 | 2020-7-30 | 2020-7-24 12:05:54 | 2020-7-24 12:06:17 | 2020-7-24 12:10:59 | 2020-7-28 10:10:47 | 2020-7-28 16:48:01 | 2020-7-29 11:10:27 | 2020-7-30 09:36:55 | 2020-7-30 09:37:13 | [6 empty] | 8.1155 | 0.0002662 | 0.0032639 | 1.0002 | 3.1922 | 0.76558 | 0.93505 | 0.00020833 | [6 empty] | 14.0123 | 5.8932 | TDC-4627 | 2020-8-20 | 6.02 | 1.8982 | 6.7447 | 13.1933 | 9.02 | 15.1708 | 46.3908
TDC-4651 | New Feature | [Back] I18N for Dataset 1.31.0-20200904142125 | 2020-8-26 |  | 2020-9-4 14:37:03 |  | 2020-9-4 14:37:07 | 2020-9-7 11:24:45 |  | 2020-9-8 15:16:19 | [8 empty] | 9.1329 |  | 4.6296e-05 | 2.8664 |  | 1.1608 | [9 empty] | 4.0272 | TDC-3991 | 2020-8-25 | 5.07 | 1.8982 | 6.7447 | 13.1933 | 123.32 | 15.1708 | 46.3908
TDC-4405 | Work Item | [QA] Production update TICO | 2020-7-7 | 2020-8-6 | 2020-7-15 09:14:22 | 2020-7-30 16:41:00 | 2020-8-5 10:13:10 | 2020-8-6 09:26:36 |  | 2020-8-6 09:26:43 |  |  |  |  | 2020-7-30 16:40:50 |  |  |  | 7.7184 | 0.00011574 | 11.9925 | 6.7446 |  | 8.1019e-05 | [6 empty] | 3.2713 |  | 29.727 | 6.7447 | TDC-4143 | 2020-8-26 | 5.94 | 1.8982 | 6.7447 | 13.1933 | 97.66 | 15.1708 | 46.3908
TDC-4415 | Work Item | [QA] Production update TICO | 2020-7-8 |  | 2020-7-29 14:10:03 | 2020-7-29 14:10:13 | [12 empty] | 20.9798 | 0.00011574 | [13 empty] | 0 | TDC-4251 | 2020-8-27 | 16.78 | 1.8982 | 6.7447 | 13.1933 | 69.98 | 15.1708 | 46.3908
TDC-4516 | Work Item | [Security] Monitoring and more | 2020-7-20 | 2020-7-29 | 2020-7-27 10:04:31 |  | 2020-7-27 10:04:36 | 2020-7-27 10:57:14 |  | 2020-7-29 10:14:09 | [8 empty] | 6.979 |  | 5.787e-05 | 0.036551 |  | 1.9701 | [8 empty] | 8.9857 | 2.0066 | TDC-4081 | 2020-9-2 | 8.14 | 1.8982 | 6.7447 | 13.1933 | 119.16 | 15.1708 | 46.3908
TDC-4406 | Work Item | [All] Test Automation debt: Increase global coverage | 2020-7-7 | 2020-7-23 | 2020-7-9 11:34:02 | 2020-7-23 14:54:44 | [8 empty] | 2020-7-23 14:54:53 |  |  |  | 1.8139 | 14.1394 | [10 empty] | 0.00010417 |  | 15.9534 | 0 | TDC-3796 | 2020-9-2 | 7.41 | 1.8982 | 6.7447 | 13.1933 | 168.97 | 15.1708 | 46.3908
TDC-4526 | Work Item | [Security] Monitoring and more | 2020-7-21 | 2020-8-20 | 2020-7-29 14:09:38 | 2020-7-29 14:09:57 | 2020-8-20 10:23:49 | 2020-8-20 10:32:19 |  | 2020-8-20 10:32:29 | [8 empty] | 7.9487 | 0.00021991 | 21.843 | 0.0059028 |  | 0.00011574 | [8 empty] | 29.7979 | 0.0060185 | TDC-4638 | 2020-9-2 | 15.82 | 1.8982 | 6.7447 | 13.1933 | 15.95 | 15.1708 | 46.3908
TDC-4563 | Work Item | [Back][Security] Bump Rating service to play 2.8 | 2020-7-28 | 2020-8-13 | 2020-7-29 14:11:12 | 2020-7-31 09:31:03 | 2020-8-4 14:25:37 | 2020-8-4 14:25:42 | 2020-8-4 14:25:46 | 2020-8-11 11:37:18 | 2020-8-12 09:46:04 | 2020-8-13 12:20:01 | [6 empty] | 1.1609 | 1.8055 | 4.2046 | 5.787e-05 | 4.6296e-05 | 6.883 | 0.92275 | 1.1069 | [6 empty] | 16.0837 | 8.9128 | TDC-4659 | 2020-9-2 | 1.36 | 1.8982 | 6.7447 | 13.1933 | 2.12 | 15.1708 | 46.3908
TDC-4602 | Work Item | [Security] Monitoring and more S50 | 2020-8-3 |  | 2020-8-21 07:49:27 |  | 2020-9-7 09:58:32 | 2020-9-7 12:07:06 | [10 empty] | 17.6862 |  | 17.0896 | 0.089282 | [11 empty] | 0.089282 | TDC-4647 | 2020-9-2 | 8.94 | 1.8982 | 6.7447 | 13.1933 | 9.13 | 15.1708 | 46.3908
TDC-4665 | Bug | XXE via File Upload to SSRF | 2020-7-6 |  | 2020-9-9 10:10:17 |  | 2020-8-19 10:11:51 | [7 empty] | 2020-8-25 13:38:39 | 2020-8-12 15:41:24 |  |  | 14.8553 |  | 6.7711 | [9 empty] | 6.1436 | 37.4133 |  | 0 | TDC-4660 | 2020-9-2 | 1.61 | 1.8982 | 6.7447 | 13.1933 | 1.61 | 15.1708 | 46.3908
TDC-4345 | Work Item | [QA] Trust score | 2020-7-1 | 2020-8-18 | 2020-7-15 09:14:12 | 2020-8-3 18:10:54 | 2020-8-5 10:08:41 | 2020-8-7 13:32:58 |  | 2020-8-17 17:11:39 | 2020-8-18 17:41:35 |  |  |  | 2020-7-31 16:30:56 |  |  |  | 13.9166 | 3.0694 | 8.713 | 4.3178 |  | 10.1519 | 1.0208 | [5 empty] | 7.0795 |  | 48.2689 | 15.4904 | TDC-4662 | 2020-9-3 | 1.93 | 1.8982 | 6.7447 | 13.1933 | 2.13 | 15.1708 | 46.3908
TDC-4518 | Work Item | [QA][UI] Stabilize ui tests | 2020-7-20 | 2020-7-20 | 2020-7-20 11:45:14 |  | 2020-7-20 11:45:22 | 2020-7-20 11:45:27 |  | 2020-7-20 11:50:18 | [8 empty] | 0.00016204 |  | 9.2593e-05 | 5.787e-05 |  | 0.0033681 | [8 empty] | 0.0036806 | 0.0034259 | TDC-4673 | 2020-9-3 | 0.07 | 1.8982 | 6.7447 | 13.1933 | 0.07 | 15.1708 | 46.3908
TDC-4556 | Bug | [Front] Redirect /Users and /account to the v2 of scim | 2020-7-27 | 2020-7-28 | 2020-7-27 17:30:45 |  | 2020-7-27 17:30:50 | 2020-7-27 17:30:53 | 2020-7-28 09:05:47 | 2020-7-28 09:05:54 | 2020-7-28 09:06:00 | 2020-7-28 11:00:09 | [6 empty] | 0.0071644 |  | 5.787e-05 | 3.4722e-05 | 0.64924 | 8.1019e-05 | 6.9444e-05 | 0.079271 | [6 empty] | 0.73591 | 0.72869 | TDC-4546 | 2020-9-7 | 11.97 | 1.8982 | 6.7447 | 13.1933 | 44.7 | 15.1708 | 46.3908
TDC-4609 | New Feature | [Frontend] Use the new datasets attribute endpoint for description and CAV | 2020-8-5 | 2020-8-19 | 2020-8-5 12:11:16 |  | 2020-8-5 15:23:08 | 2020-8-6 15:08:23 | 2020-8-6 16:46:49 | 2020-8-14 00:51:13 | 2020-8-19 10:00:01 | 2020-8-19 16:14:53 | [6 empty] | 0.096875 |  | 0.13324 | 0.98976 | 0.068356 | 7.3364 | 5.3811 | 0.26032 | [6 empty] | 14.2661 | 14.0359 | TDC-4604 | 2020-9-7 | 11 | 1.8982 | 6.7447 | 13.1933 | 34.77 | 15.1708 | 46.3908
TDC-4627 | Work Item | [Back] Trust score - Add unit tests by axis | 2020-8-11 | 2020-8-20 | 2020-8-14 16:04:34 |  | 2020-8-14 16:04:38 | 2020-8-19 17:44:59 | 2020-8-20 16:34:27 | 2020-8-20 16:34:39 | [8 empty] | 2.9942 |  | 4.6296e-05 | 5.0697 | 0.95102 | 0.00013889 | [8 empty] | 9.0151 | 6.0208 | TDC-4536 | 2020-9-7 | 11.98 | 1.8982 | 6.7447 | 13.1933 | 45.8 | 15.1708 | 46.3908
TDC-4638 | Bug | [Front] Clicking on dataset tab remove the filter form the URL | 2020-8-17 | 2020-9-2 | 2020-8-17 19:33:46 |  | 2020-8-17 19:33:53 | 2020-8-17 19:34:38 | 2020-8-18 17:27:26 | 2020-9-1 11:14:16 | 2020-9-2 15:13:03 | 2020-9-2 15:15:38 | [6 empty] | 0.13109 |  | 8.1019e-05 | 0.00052083 | 0.91167 | 13.7409 | 1.1658 | 0.001794 | [6 empty] | 15.9518 | 15.8207 | TDC-4611 | 2020-9-7 | 3.79 | 1.8982 | 6.7447 | 13.1933 | 33.02 | 15.1708 | 46.3908
TDC-4664 | Bug | [Back] The semantic type are not detected on DataType = Date | 2020-9-1 |  | 2020-9-4 10:45:21 |  | 2020-9-4 10:45:26 | 2020-9-4 16:07:11 |  | 2020-9-7 16:14:44 | [8 empty] | 2.7628 |  | 5.787e-05 | 0.22344 |  | 3.0052 | [9 empty] | 3.2287 | TDC-4652 | 2020-9-7 | 10 | 1.8982 | 6.7447 | 13.1933 | 11.03 | 15.1708 | 46.3908
TDC-4666 | Bug | CE4D is down on EAP | 2020-9-1 | 2020-9-4 | 2020-9-2 10:05:24 |  | 2020-9-4 10:19:17 | [11 empty] | 0.43962 |  | 2.0096 | [11 empty] | 2.4493 | 0 | TDC-4667 | 2020-9-7 | 3.78 | 1.8982 | 6.7447 | 13.1933 | 4.96 | 15.1708 | 46.3908
TDC-4544 | Work Item | [Release] Data Inventory 1.26.0 | 2020-7-24 | 2020-7-28 | 2020-7-24 12:46:02 |  | 2020-7-24 12:46:09 | 2020-7-24 12:46:15 |  | 2020-7-27 14:20:08 | 2020-7-27 17:17:55 | 2020-7-28 11:58:10 | [6 empty] | 0.046771 |  | 8.1019e-05 | 6.9444e-05 |  | 3.0652 | 0.12346 | 0.77795 | [6 empty] | 4.0135 | 3.9667
TDC-4520 | Work Item | [Release] Dataset 1.28.0 | 2020-7-20 | 2020-7-28 | 2020-7-20 17:36:39 |  | 2020-7-20 17:36:46 | 2020-7-20 17:36:55 |  | 2020-7-21 21:25:39 | 2020-7-22 14:43:19 | 2020-7-28 09:46:59 | [6 empty] | 0.019016 |  | 8.1019e-05 | 0.00010417 |  | 1.1588 | 0.7206 | 5.7942 | [6 empty] | 7.6929 | 7.6738
TDC-4559 | Work Item | [Release] Data Inventory 1.24.2 | 2020-7-27 | 2020-7-28 | 2020-7-28 08:40:12 |  | 2020-7-28 08:40:17 | 2020-7-28 08:40:24 |  | 2020-7-28 09:12:18 | 2020-7-28 09:12:23 | 2020-7-28 11:04:44 | [6 empty] | 0.58797 |  | 5.787e-05 | 8.1019e-05 |  | 0.022153 | 5.787e-05 | 0.078021 | [6 empty] | 0.68834 | 0.10031
TDC-4597 | Work Item | [Release] Dataset 1.29.1 | 2020-7-31 | 2020-8-4 | 2020-7-31 16:38:11 |  | 2020-7-31 16:38:21 | 2020-7-31 16:38:30 |  | 2020-8-3 16:44:25 | 2020-8-3 17:48:00 | 2020-8-4 17:37:00 | [6 empty] | 0.29222 |  | 0.00011574 | 0.00010417 |  | 3.0041 | 0.044155 | 0.99236 | [6 empty] | 4.3331 | 4.0407
TDC-4659 | Work Item | [release] Data Inventory GW 1.29.0 | 2020-8-31 | 2020-9-2 | 2020-9-1 10:44:44 |  | 2020-9-1 10:44:49 | 2020-9-1 10:44:54 |  | 2020-9-2 09:32:24 | 2020-9-2 15:12:04 | 2020-9-2 19:25:40 | [6 empty] | 0.75591 |  | 5.787e-05 | 5.787e-05 |  | 0.94965 | 0.23588 | 0.17611 | [6 empty] | 2.1177 | 1.3617
TDC-4607 | New Feature | [Engineering] Craft trust score formula V2 | 2020-8-4 | 2020-8-7 | 2020-8-4 10:48:41 |  | 2020-8-4 11:05:51 | 2020-8-4 11:50:39 |  | 2020-8-7 10:12:15 | [8 empty] | 0.00023148 |  | 0.011921 | 0.031111 |  | 2.9317 | [8 empty] | 2.9749 | 2.9628
TDC-4342 | Bug | Semantic Type not found | 2020-6-30 | 2020-7-24 | 2020-7-21 11:01:57 |  | 2020-7-21 11:02:02 | 2020-7-21 17:37:10 |  | 2020-7-21 17:45:12 | 2020-7-24 14:30:50 | 2020-7-24 14:31:00 | [6 empty] | 20.979 |  | 5.787e-05 | 0.2744 |  | 0.0055787 | 0.99635 | 1.8688 | [6 empty] | 24.1242 | 3.1451
TDC-4611 | Work Item | [Back] I18N for Dataset 1.29.1-20200803170109 | 2020-8-5 | 2020-9-7 | 2020-9-3 16:13:00 |  | 2020-9-3 16:13:06 | 2020-9-3 16:13:43 |  | 2020-9-4 15:52:56 | 2020-9-7 11:11:01 | [7 empty] | 29.227 |  | 6.9444e-05 | 0.00042824 |  | 0.98557 | 2.8042 | [7 empty] | 33.0173 | 3.7902
TDC-4519 | Bug | [Sharing] sharingset hard deletion issues | 2020-7-20 | 2020-7-24 | 2020-7-21 10:20:15 |  | 2020-7-21 10:20:19 | 2020-7-23 15:09:31 | 2020-7-23 16:40:37 | 2020-7-24 10:32:14 | 2020-7-24 14:54:51 | 2020-7-24 16:56:47 | [6 empty] | 0.72368 |  | 4.6296e-05 | 0.0021412 | 2.0782 | 0.92789 | 0.18237 | 0.084676 | [6 empty] | 3.9991 | 3.2753
TDC-4498 | Bug | Semantic Type Not Populating | 2020-7-15 | 2020-7-24 | 2020-7-21 09:05:40 |  | 2020-7-21 09:05:47 | 2020-7-21 09:05:52 |  | 2020-7-21 11:02:26 | 2020-7-24 14:29:52 | 2020-7-24 14:30:02 | [6 empty] | 5.5723 |  | 8.1019e-05 | 5.787e-05 |  | 0.080949 | 2.0244 | 1.1198 | [6 empty] | 8.7976 | 3.2252
TDC-4538 | Bug | Sharing hard deletion introduces a security issue | 2020-7-23 | 2020-7-24 | 2020-7-23 16:39:22 |  | 2020-7-23 16:39:25 | 2020-7-23 16:39:33 | 2020-7-23 16:58:13 | 2020-7-24 10:03:26 | 2020-7-24 14:54:43 | 2020-7-24 16:58:48 | [6 empty] | 0.0099537 |  | 3.4722e-05 | 9.2593e-05 | 0.012963 | 0.71196 | 0.20228 | 0.086169 | [6 empty] | 1.0234 | 1.0135
TDC-4557 | Work Item | [Release] Data Inventory 1.26.1 | 2020-7-27 | 2020-7-28 | 2020-7-28 09:13:18 | [13 empty] | 0.63508 | [13 empty] | 0.63508 | 0
TDC-4542 | Bug | [Back] Faceted search : Too many operators for 'number-in-range' ('slider') facets | 2020-7-24 | 2020-7-30 | 2020-7-29 10:41:31 |  | 2020-7-29 10:41:40 | 2020-7-29 10:41:46 | 2020-7-29 14:38:24 | 2020-7-29 22:46:38 | 2020-7-30 16:45:42 | 2020-7-30 18:05:56 | [6 empty] | 4.9824 |  | 0.00010417 | 6.9444e-05 | 0.16433 | 0.33905 | 0.74935 | 0.055718 | [6 empty] | 6.291 | 1.3085
TDC-4543 | Bug | [Back] Invalid, Valid, and Empty facets labels are wrong | 2020-7-24 | 2020-7-31 | 2020-7-29 10:42:01 |  | 2020-7-29 10:42:06 | 2020-7-29 10:42:11 | 2020-7-29 14:38:34 | 2020-7-29 17:01:25 | 2020-7-30 16:45:50 | 2020-7-31 08:01:00 | [6 empty] | 4.9804 |  | 5.787e-05 | 5.787e-05 | 0.16416 | 0.099201 | 0.98918 | 0.63553 | [6 empty] | 6.8686 | 1.8881
TDC-4577 | Work Item | [Release] Dataset 1.29.0 | 2020-7-29 | 2020-7-31 | 2020-7-29 14:35:46 |  | 2020-7-29 14:35:58 | 2020-7-29 14:36:04 |  | 2020-7-30 14:12:21 | 2020-7-30 14:12:26 | 2020-7-31 16:30:13 | [6 empty] | 0.10991 |  | 0.00013889 | 6.9444e-05 |  | 0.98353 | 5.787e-05 | 1.0957 | [6 empty] | 2.1894 | 2.0793
TDC-4621 | Work Item | [Release] Rating 1.16.0 | 2020-8-10 | 2020-8-13 | 2020-8-10 15:41:19 |  | 2020-8-10 15:41:27 | 2020-8-10 16:27:07 |  | 2020-8-11 11:38:45 | 2020-8-12 09:46:09 | 2020-8-13 12:20:43 | [6 empty] | 0.18057 |  | 9.2593e-05 | 0.031713 |  | 0.79975 | 0.92181 | 1.1073 | [6 empty] | 3.0413 | 2.8606
TDC-4622 | Work Item | [Release] dataset-ui 32.1.0 | 2020-8-10 | 2020-8-10 | 2020-8-10 15:44:26 | [13 empty] | 0.018206 | [13 empty] | 0.018206 | 0
TDC-4623 | Work Item | [Release] data-catalog 1.28.0 | 2020-8-10 | 2020-8-19 | 2020-8-10 15:41:53 |  | 2020-8-10 15:42:01 | 2020-8-10 16:31:55 |  | 2020-8-14 00:55:30 | 2020-8-19 10:00:08 | 2020-8-19 16:16:11 | [6 empty] | 0.013102 |  | 9.2593e-05 | 0.034653 |  | 3.3497 | 5.3782 | 0.26115 | [6 empty] | 9.0369 | 9.0237
TDC-4624 | Work Item | [Frontend] Can't delete description | 2020-8-10 | 2020-8-19 | 2020-8-10 20:19:56 |  | 2020-8-10 20:20:14 | 2020-8-10 20:21:04 | 2020-8-11 10:50:32 | 2020-8-14 00:54:05 | 2020-8-19 10:17:17 | 2020-8-19 16:14:11 | [6 empty] | 0.0139 |  | 0.00020833 | 0.0005787 | 0.6038 | 2.5858 | 5.3911 | 0.24785 | [6 empty] | 8.8432 | 8.8291
TDC-4625 | Work Item | [Frontend] No user feedback when editing the dataset description for the first time | 2020-8-10 | 2020-8-19 | 2020-8-10 20:22:34 |  | 2020-8-10 20:22:48 | 2020-8-10 20:22:55 | 2020-8-11 10:50:21 | 2020-8-14 00:55:09 | 2020-8-19 10:00:24 | 2020-8-19 16:15:39 | [6 empty] | 0.013762 |  | 0.00016204 | 8.1019e-05 | 0.60238 | 2.5867 | 5.3786 | 0.26059 | [6 empty] | 8.8423 | 8.8284
TDC-4632 | Work Item | [Release] Dataset 1.30.0 | 2020-8-14 | 2020-8-18 | 2020-8-17 10:47:51 |  | 2020-8-17 10:48:07 | 2020-8-17 10:48:15 |  | 2020-8-17 17:02:03 | 2020-8-18 17:39:30 | 2020-8-18 17:39:41 | [6 empty] | 2.9996 |  | 0.00018519 | 9.2593e-05 |  | 0.25958 | 1.026 | 0.00012731 | [6 empty] | 4.2856 | 1.2858
TDC-4647 | Bug | [Front] Local connection creation fails while drag&drop if at least one engine has issues | 2020-8-24 | 2020-9-2 | 2020-8-24 16:34:59 |  | 2020-8-24 16:35:05 | 2020-8-24 16:35:10 | 2020-8-31 10:16:06 | 2020-9-1 11:26:44 | 2020-9-2 15:12:38 | 2020-9-2 15:12:52 | [6 empty] | 0.19198 |  | 6.9444e-05 | 5.787e-05 | 6.7368 | 1.0491 | 1.1569 | 0.00016204 | [6 empty] | 9.135 | 8.9429
TDC-4652 | Bug | [Back] Retrieve trust score metrics built-in attributes from samples on dataset retrieval, if missing. | 2020-8-27 | 2020-9-7 | 2020-8-27 10:37:06 |  | 2020-8-28 09:54:37 | 2020-9-1 11:37:03 | 2020-9-1 11:51:25 | 2020-9-3 18:20:19 | 2020-9-7 09:50:00 | 2020-9-7 09:51:16 | [6 empty] | 0.061574 |  | 0.9705 | 4.0711 | 0.0099769 | 2.2701 | 3.6456 | 0.00087963 | [6 empty] | 11.0297 | 9.9977
TDC-4660 | Work Item | [QA] [UI] implementing new scenario for filtering datasets by tag | 2020-8-31 | 2020-9-2 | 2020-8-31 18:58:35 |  | 2020-8-31 18:58:43 | 2020-8-31 18:58:48 |  | 2020-9-2 09:30:50 | [8 empty] | 0.0002662 |  | 9.2593e-05 | 5.787e-05 |  | 1.6056 | [8 empty] | 1.606 | 1.6056
TDC-4667 | Work Item | [Release] Dataset 1.31.0 | 2020-9-2 | 2020-9-7 | 2020-9-3 16:24:13 |  | 2020-9-3 16:24:18 | 2020-9-3 16:24:23 |  | 2020-9-4 12:05:09 | 2020-9-7 11:12:45 | 2020-9-7 11:12:53 | [6 empty] | 1.1808 |  | 5.787e-05 | 5.787e-05 |  | 0.81998 | 2.9636 | 9.2593e-05 | [6 empty] | 4.9646 | 3.7837
TDC-4673 | Work Item | [QA] [UI] Maintain the scenario "Preview the sample of the dataset upon creation" | 2020-9-3 | 2020-9-3 | 2020-9-3 12:22:23 |  | 2020-9-3 12:22:28 | 2020-9-3 12:22:32 |  | 2020-9-3 14:08:21 | [8 empty] | 0.00011574 |  | 5.787e-05 | 4.6296e-05 |  | 0.073484 | [8 empty] | 0.073704 | 0.07353
TDC-4679 | Work Item | [Release] Dataset 1.32.0 | 2020-9-7 |  | 2020-9-7 11:15:59 |  | 2020-9-7 11:16:03 | 2020-9-7 11:24:57 |  | 2020-9-8 15:36:39 | 2020-9-9 10:39:39 | [7 empty] | 0.0085301 |  | 4.6296e-05 | 0.0061806 |  | 1.1748 | 0.79375 | [8 empty] | 1.9747