## Raw_Metrics
Issue key | Issue Type | Issue Summary | Creation Date | Resolution Date | In New Date | In Candidate Date | In Accepted Date | In in progress Date | In Code review Date | In Validation Date | In Merge Date | In Final check Date | In Done Date | In Closed Date | In On hold Date | In To Do Date | In Blocked Date | In Rejected Date | In New Time | In Candidate Time | In Accepted Time | In in progress Time | In Code review Time | In Validation Time | In Merge Time | In Final check Time | In Done Time | In Closed Time | In Blocked Time | In Rejected Time | In On hold Time | In To Do Time | Lead time
TDC-4662 | Work Item | [QA][SRE] AKS VMSS migration / DNS Switch to TPSVC services on K8s | 2020-9-1 12:38:40 |  | 2020-9-1 12:38:40
TDC-4081 | Bug | [Front] The raw sample view is not fed with the right data | 2020-5-6 11:26:57 |  | 2020-7-24 16:00:09 | 2020-8-7 11:57:36 | 2020-8-25 11:57:32 | 2020-8-26 11:42:26 | 2020-8-26 14:29:37 | [9 empty] | 79 Days 04:33:11 | 13 Days 19:57:27 | 17 Days 23:59:55 | 0 Days 23:44:54 | 0 Days 02:47:11
TDC-4642 | Work Item | [Back] Add schema to dataset-samples response | 2020-8-20 12:08:47 |  | 2020-8-20 16:18:14 |  | 2020-9-1 11:59:36 | [11 empty] | 0 Days 04:09:26 |  | 11 Days 19:41:21
TDC-3796 | New Feature | [Front] Improve Pendo Analytics | 2020-3-17 19:02:27 |  | 2020-7-28 11:54:53 | 2020-8-7 10:58:04 | 2020-8-26 09:42:06 | 2020-8-26 09:42:18 | 2020-8-28 10:10:39 | [5 empty] | 2020-7-28 11:45:36 |  |  |  | 13 Days 13:22:37 | 9 Days 23:03:11 | 18 Days 22:44:02 | 0 Days 00:00:11 | 2 Days 00:28:20 | [7 empty] | 119 Days 02:29:49
TDC-4143 | Bug | [Front] Form freezes when editing a shared dataset as READER using Local Connection | 2020-5-20 22:55:31 | 2020-8-26 14:40:37 | 2020-7-24 16:44:36 | 2020-8-7 15:49:50 | 2020-8-20 16:07:04 | 2020-8-26 14:40:01 |  | 2020-8-26 14:40:37 | [8 empty] | 64 Days 17:49:04 | 13 Days 23:05:14 | 13 Days 00:17:13 | 0 Days 00:08:37 |  | 5 Days 22:24:56 | [8 empty] | 97 Days 15:45:06
TDC-4634 | Bug | SSRF on Data Inventory leaking AWS metadata | 2020-7-2 03:21:23 | 2020-8-17 11:25:23 | 2020-8-14 18:16:36 | 2020-8-17 07:51:15 | 2020-8-17 11:24:48 | 2020-8-17 11:24:54 |  | 2020-8-17 11:25:23 |  |  | 2020-8-28 15:26:02 |  |  | 2020-8-14 17:53:10 |  |  | 0 Days 00:23:26 | 2 Days 13:34:39 | 0 Days 03:33:33 | 0 Days 00:00:05 |  | 0 Days 00:00:29 |  |  | 11 Days 04:00:38 |  |  |  |  | 43 Days 14:31:46 | 46 Days 08:03:59
TDC-3991 | Bug | [Back] Element in a list starting with $ raise a cast exception | 2020-4-24 09:46:30 | 2020-8-25 17:31:08 | 2020-7-24 16:12:48 | 2020-8-5 16:35:10 | 2020-8-20 15:51:34 | 2020-8-20 15:51:39 |  | 2020-8-25 17:31:08 | [8 empty] | 91 Days 06:26:18 | 12 Days 00:22:22 | 14 Days 23:16:23 | 0 Days 00:00:05 |  | 5 Days 01:39:28 | [8 empty] | 123 Days 07:44:37
TDC-4251 | New Feature | [Front] [Security] Automate SCA & SAST scans. | 2020-6-18 10:44:32 | 2020-8-27 10:16:38 | 2020-7-30 15:49:46 | 2020-7-30 15:49:56 | 2020-8-10 15:38:55 | 2020-8-20 10:00:07 | 2020-8-27 10:16:23 | 2020-8-27 10:16:38 | [8 empty] | 42 Days 05:05:14 | 0 Days 00:00:10 | 10 Days 23:48:59 | 9 Days 18:21:11 | 7 Days 00:16:16 | 0 Days 00:00:15 | [8 empty] | 69 Days 23:32:06
TDC-4603 | Work Item | [Provisioning Sprint 50] Manage unexpected / unplanned subjects | 2020-8-3 15:22:47 |  | 2020-8-21 07:53:49 | [13 empty] | 17 Days 16:31:02
TDC-4194 | New Feature | [Back][Attributes] Create/Update CAV automatically when CAD default value is settled/updated | 2020-6-8 15:09:47 |  | 2020-6-30 16:45:57 | 2020-8-5 15:43:24 | 2020-8-25 11:51:26 | 2020-8-28 17:36:25 | [10 empty] | 22 Days 01:36:10 | 35 Days 22:57:26 | 19 Days 20:08:02 | 3 Days 05:44:58
TDC-4546 | New Feature | [Back] Trust score Formula V2 : enrichment with description, tags and attributes | 2020-7-24 16:58:46 |  | 2020-8-20 15:24:07 | 2020-8-20 15:25:30 | 2020-8-26 10:31:17 | 2020-8-31 09:42:52 | [10 empty] | 26 Days 22:25:20 | 0 Days 00:01:23 | 5 Days 19:05:47 | 4 Days 23:11:34
TDC-4604 | Work Item | [QA] Trust score Formula V2: Automate Validation Tests | 2020-8-3 15:40:28 |  | 2020-8-17 16:09:09 |  | 2020-8-27 10:03:43 | 2020-8-31 01:54:15 | [10 empty] | 14 Days 00:28:41 |  | 9 Days 17:54:33 | 3 Days 15:50:31
TDC-4605 | New Feature | [TUI][Front] Trust score data visualization | 2020-8-3 15:59:58 |  | 2020-8-26 09:08:44 |  | 2020-8-31 10:08:43 | [11 empty] | 22 Days 17:08:46 |  | 5 Days 00:59:59
TDC-4536 | New Feature | [Back] Trust score api payload with axes. | 2020-7-23 14:35:23 |  | 2020-8-20 15:38:06 |  | 2020-8-26 10:21:09 | 2020-8-27 10:18:01 | 2020-8-31 17:00:46 | [9 empty] | 28 Days 01:02:43 |  | 5 Days 18:43:03 | 0 Days 23:56:51 | 4 Days 06:42:44
TDC-4572 | Work Item | [Back] [Engineering] Trust score V3 : enrichment with new metrics | 2020-7-28 18:29:47 |  | 2020-8-4 17:52:45 | [13 empty] | 6 Days 23:22:57
TDC-4651 | New Feature | [i18N][Back] Trust score api label and description i18n | 2020-8-26 11:25:44 |  | 2020-8-26 11:25:44
TDC-4415 | Work Item | [QA] Production update TICO | 2020-7-8 14:39:04 |  | 2020-7-29 14:10:03 | 2020-7-29 14:10:13 | [12 empty] | 20 Days 23:30:58 | 0 Days 00:00:10
TDC-4602 | Work Item | [Security] Monitoring and more S50 | 2020-8-3 15:21:20 |  | 2020-8-21 07:49:27 | [13 empty] | 17 Days 16:28:06
TDC-4627 | Work Item | [Back] Trust score - Add unit tests by axis | 2020-8-11 16:12:58 | 2020-8-20 16:34:39 | 2020-8-14 16:04:34 |  | 2020-8-14 16:04:38 | 2020-8-19 17:44:59 | 2020-8-20 16:34:27 | 2020-8-20 16:34:39 | [8 empty] | 2 Days 23:51:35 |  | 0 Days 00:00:04 | 5 Days 01:40:20 | 0 Days 22:49:28 | 0 Days 00:00:11 | [8 empty] | 9 Days 00:21:40
TDC-4659 | Work Item | [release] Data Inventory GW 1.29.0 | 2020-8-31 16:36:13 |  | 2020-9-1 10:44:44 |  | 2020-9-1 10:44:49 | 2020-9-1 10:44:54 | [10 empty] | 0 Days 18:08:30 |  | 0 Days 00:00:05 | 0 Days 00:00:05
TDC-4647 | Bug | [Front] Local connection creation fails while drag&drop if at least one engine has issues | 2020-8-24 11:58:32 |  | 2020-8-24 16:34:59 |  | 2020-8-24 16:35:05 | 2020-8-24 16:35:10 | 2020-8-31 10:16:06 | 2020-9-1 11:26:44 | [8 empty] | 0 Days 04:36:26 |  | 0 Days 00:00:05 | 0 Days 00:00:05 | 6 Days 17:40:56 | 1 Days 01:10:38
TDC-4638 | Bug | [Front] Clicking on dataset tab remove the filter form the URL | 2020-8-17 16:25:00 |  | 2020-8-17 19:33:46 |  | 2020-8-17 19:33:53 | 2020-8-17 19:34:38 | 2020-8-18 17:27:26 | 2020-9-1 11:14:16 | [8 empty] | 0 Days 03:08:45 |  | 0 Days 00:00:07 | 0 Days 00:00:45 | 0 Days 21:52:47 | 13 Days 17:46:49
TDC-4652 | Bug | [Back] Retrieve trust score metrics built-in attributes from samples on dataset retrieval, if missing. | 2020-8-27 09:08:26 |  | 2020-8-27 10:37:06 |  | 2020-8-28 09:54:37 | 2020-9-1 11:37:03 | 2020-9-1 11:51:25 | [9 empty] | 0 Days 01:28:40 |  | 0 Days 23:17:31 | 4 Days 01:42:25 | 0 Days 00:14:21
TDC-4660 | Work Item | [QA] [UI] implementing new scenario for filtering datasets by tag | 2020-8-31 18:58:12 |  | 2020-8-31 18:58:35 |  | 2020-8-31 18:58:43 | 2020-8-31 18:58:48 | [10 empty] | 0 Days 00:00:23 |  | 0 Days 00:00:08 | 0 Days 00:00:05